## Sheet1
# | Name# | Skill sets and area | Artifacts to be produced | End Goal | Timeline | Latest status as on 5/22 | Latest status as on 5/23 | Latest status as on 5/24 | Latest status as on 5/27 | Latest status as on 5/28 | Latest status as on 5/29 | Latest status as on 5/30 | Latest status as on 5/31 | Latest status as on 6/03 | Latest status as on 6/04 | Latest status as on 6/05 | Latest status as on 6/06
1 | Srinivas | Selenium framework, Jenkins and DevOps | 1. Architecture diagram and documentation for framework. 2. framework itself including devops components. | Publish framework that works with Jenkins and GitHub | 1. Architecture diagram and documentation for framework : 29th May'19 2. framework itself including devops components : 4th Jun'19 | 1. POM framework is ready with sample test cases. 2. Created an sampleMaven Project with BDD framework. | 1. STAF framework is imported 2. Installtion process is in progress 3. Maven errors are being resolved | 1. STAF framework is imported 2. Installtion process is in progress 3. Maven errors are being resolved | 1. STAF framework is in progress 2. Adhoc Request that are worked for Today : 1. Consolidated “Testing Achievements - 2018-19” for STR 2. In search and worked on “Reference applications for the POC/Demos” which is requested by Abhishek | 1. Tried the all possibility of free webapp db connection 2. Attended Unix/Linux session. 3. Completed and attached the simple POM+Log4j +TestNg framework. | 1. Documentation of POM framework. 2. Uploaded the document of POM framework to Github. 3. Tried to connect the sample web application to database. | 1. Documentation of POM framework. 2. Uploaded the document of POM framework to Github. 3. Tried to connect the sample web application to database. | 1. Documentation of POM framework. 2. Uploaded the document of POM framework to Github. 3. Tried to connect the sample web application to database. | Demo preparation and started working on cucumber framework | 1. Implimented running test suite through Jenkins (Through Windows Slave). | 1. Implemented Jenkins with parallel browser testing. | 1. IN PROGRESS- Adding the git repository to Jenkins. 2. Cucumber framework with Data Driven and POM is in progress.
2 | Nikhil | Selenium framework, Jenkins and DevOps | 1. Architecture diagram and documentation for framework. 2. framework itself including devops components. | Publish framework that works with Jenkins and GitHub | 1. Architecture diagram and documentation for framework : 29th May'19 2. framework itself including devops components : 4th Jun'19 | 1. POM framework is ready with sample test cases. 2. Created an sampleMaven Project with BDD framework. | Automated the login page by identifying the page elements into one class and tried to automate the login functionality | 1. Today I tried to add a book to the shopping cart and complete the order. 2. For that I have identified all the required page elements into different classes and started writing the step definitions. 3. Writing of step definitions is in progress. | Completed writing step definitions and facing exceptions while executing. Resolving in progress | > Resolving exceptions is in progress. > Attended UNIX session by kamna > Tried to connect the sample web application to the database. | 1. Resolved the exceptions faced earlier. 2. Added two more features to the feature file and step definition writing for the same is in progress. | 1. completed writing the stepdefinitions. 2. worked with srini in connecting the sample web application. | 1. completed an end2end flow of adding a book to cart and completing the order. 2. Input was taken by the hardcoded values. | 1. Completed an end 2 end flow using CUCUMBER framework. 2. Trying to take the input from an excel sheet where ever input is required. | 1. Added code to capture screenshot on a scenario failure. 2. Tried to add code for extent report generation, but facing some exceptions. Trying to resolve them. | 1. Extent report generation is still in progress. 2. Still working on accepting data from the excel sheet. | 1. Implemented extent reports in the project and reports are getting generated as per the result. 2. Trying to add the screenshots in failure case to the extent reports. 3. Accepting input from the excel sheet is still in progress.
3 | Ramesh | UFT framework and Python | 1. Generic UFT framework for webservices or any web application 2. Self Learning Python and Should be preparing an understanding document | 1. Publishing framework( Provided UFT License is there) 2. Would be ready to take up any project related to python | 1. 15 to 20 Days 2. 25 to 30 Days | This is an update from Ramesh on the today's task across email. Same is copied below: Currently I am going through Python Video’s and other articles related to python. Apart from that, I shall prepare “Basic SQL concepts and documentation for the same with examples “ by 28th May. |  |  | Python – Learned data types of python – Lists , Tuples and Practiced it declaring the same. | Learned Python Arithmetic and Assignment operators & practiced the same by writing small programs. | 1. Working on UIPath with Junaid. | 1. Working on UIPath with Junaid. | 1. Working on UIPath with Junaid. | Email Automation with RPA and Exploring REFramework | ON LEAVE | 1. Excel and Data Table Automation. | 1. Reading Email and Deleting automatically through RPA.
4 | Junaid | Testing concepts ,Python ,Machine Learning POC | Documentation of core Machine learning concepts and R, Documentation of Modeling Using R function and libraries | POC of Modeling and Implementations of Machine Learning algorithms. | 1. POC : 7th June | R Basics And Data Types - Arrays, List,Vectors,Operations,Data Frames and Descriptive Statistics |  | Introduction to RPA, Introduction to UI Path and Installed UI path tool | * UiPath – Understanding User Interface Components *Recording and Playback functionality. *Automating the task of copying data from a website and writing into excel file. | *Variables, Data Types and Activities in Ui Path *Basic exercises in UI Path studio | 1. Explored RE Framework Concepts in UI Path. | 1. Explored RE Framework Concepts in UI Path. | 1. Explored RE Framework Concepts in UI Path. | UIPATH STUDIO – DATA SCRAPING AND SCREEN SCRAPING | UiPath PDF Data Extraction and OCR Data Extraction | ON LEAVE | ON LEAVE
5 | Kamna | Database testing/ETL Testing, Jmeter,Selenium Framework | 1. KT Documents/Class Room session for ETL Testing 2. Jmeter : Process to setup the project and Documentaion | 1. KT Documents/Class Room session for ETL Testing 2. Jmeter : Process to setup the project and Documentaion | 1. ETL Testing : 28th May'19 2. Jmeter : 5th Jun'19 | 1. Git Hub repository creation 2. KT on GitHub to team Action Item for tomorrow : 1. Documentation for GitHub | On Leave | GiTHub document is added and sent for Review. Working DatabaseTesting related document with Ramesh | Working on Database testing document. Studying shell Scripting. I have scheduled a unix session . | Learning shell scripting/PPT preparation/Demo | 1. Learning Jmeter and its features/functionality used for performance testing. 2. Once done with all Jmeter feature will start POC and will design framework. | Practicing Selenium Framework using maven/TestNG/POM have uploaded the same in GIT as FirstMavenProject | Jmeter and its features/functionality used for performance/load testing. | Jmeter and its plugin manager( for Selenium Webdriver Support) also how to showing the performance dashboard in using non gui mode | 1. Was working on CI of Selenium Java project using Maven GIT Jenkins. 2. Was looking for Selenium and Jmeter framework. Couldnt find any useful tip. | 1. Jmeter PPT preparation.
6 | Shanth | RPA Automation, DevOps stacks involving selenium automation | RPA primer for the team to get started on using RPA tool(UiPath), User friendly documentation for the team to use in house published STAF framework for selenium automation | Build team capability to work on UiPath RPA tool, Provide inhouse expertise to leverage published automation framework for open source selenium along with Jenkins and Github integration | 1. RPA primer -31st May 2. STAF framework -7th June