## Sheet1
# | Name# | Skill sets and area | Artifacts to be produced | End Goal | Timeline | Latest status as on 5/22 | Latest status as on 5/23 | Latest status as on 5/24 | Latest status as on 5/27 | Latest status as on 5/28 | Latest status as on 5/29 | Latest status as on 5/30 | Latest status as on 5/31 | Latest status as on 6/03 | Latest status as on 6/04 | Latest status as on 6/05
1 | Srinivas | Selenium framework, Jenkins and DevOps | 1. Architecture diagram and documentation for framework. 2. framework itself including devops components. | Publish framework that works with Jenkins and GitHub | 1. Architecture diagram and documentation for framework : 29th May'19 2. framework itself including devops components : 4th Jun'19 | 1. POM framework is ready with sample test cases. 2. Created an sampleMaven Project with BDD framework. | 1. STAF framework is imported 2. Installtion process is in progress 3. Maven errors are being resolved | 1. STAF framework is imported 2. Installtion process is in progress 3. Maven errors are being resolved | 1. STAF framework is in progress 2. Adhoc Request that are worked for Today : 1. Consolidated “Testing Achievements - 2018-19” for STR 2. In search and worked on “Reference applications for the POC/Demos” which is requested by Abhishek | 1. Tried the all possibility of free webapp db connection 2. Attended Unix/Linux session. 3. Completed and attached the simple POM+Log4j +TestNg framework. | 1. Documentation of POM framework. 2. Uploaded the document of POM framework to Github. 3. Tried to connect the sample web application to database. | 1. Documentation of POM framework. 2. Uploaded the document of POM framework to Github. 3. Tried to connect the sample web application to database. | 1. Documentation of POM framework. 2. Uploaded the document of POM framework to Github. 3. Tried to connect the sample web application to database. | Demo preparation and started working on cucumber framework | 1. Implimented running test suite through Jenkins (Through Windows Slave). | 1. Implemented Jenkins with parallel browsing testing.
2 | Nikhil | Selenium framework, Jenkins and DevOps | 1. Architecture diagram and documentation for framework. 2. framework itself including devops components. | Publish framework that works with Jenkins and GitHub | 1. Architecture diagram and documentation for framework : 29th May'19 2. framework itself including devops components : 4th Jun'19 | 1. POM framework is ready with sample test cases. 2. Created an sampleMaven Project with BDD framework. | Automated the login page by identifying the page elements into one class and tried to automate the login functionality | 1. Today I tried to add a book to the shopping cart and complete the order. 2. For that I have identified all the required page elements into different classes and started writing the step definitions. 3. Writing of step definitions is in progress. | Completed writing step definitions and facing exceptions while executing. Resolving in progress | > Resolving exceptions is in progress. > Attended UNIX session by kamna > Tried to connect the sample web application to the database. | 1. Resolved the exceptions faced earlier. 2. Added two more features to the feature file and step definition writing for the same is in progress. | 1. completed writing the stepdefinitions. 2. worked with srini in connecting the sample web application. | 1. completed an end2end flow of adding a book to cart and completing the order. 2. Input was taken by the hardcoded values. | 1. Completed an end 2 end flow using CUCUMBER framework. 2. Trying to take the input from an excel sheet where ever input is required. | 1. Added code to capture screenshot on a scenario failure. 2. Tried to add code for extent report generation, but facing some exceptions. Trying to resolve them. | 1. Extent report generation is still in progress. 2. Still working on accepting data from the excel sheet.
3 | Ramesh | UFT framework and Python | 1. Generic UFT framework for webservices or any web application 2. Self Learning Python and Should be preparing an understanding document | 1. Publishing framework( Provided UFT License is there) 2. Would be ready to take up any project related to python | 1. 15 to 20 Days 2. 25 to 30 Days | This is an update from Ramesh on the today's task across email. Same is copied below: Currently I am going through Python Video’s and other articles related to python. Apart from that, I shall prepare “Basic SQL concepts and documentation for the same with examples “ by 28th May. |  |  | Python – Learned data types of python – Lists , Tuples and Practiced it declaring the same. | Learned Python Arithmetic and Assignment operators & practiced the same by writing small programs. | 1. Working on UIPath with Junaid. | 1. Working on UIPath with Junaid. | 1. Working on UIPath with Junaid. | Email Automation with RPA and Exploring REFramework | ON LEAVE | 1. Excel and Data Table Automation.
4 | Junaid | Testing concepts ,Python ,Machine Learning POC | Documentation of core Machine learning concepts and R, Documentation of Modeling Using R function and libraries | POC of Modeling and Implementations of Machine Learning algorithms. | 1. POC : 7th June | R Basics And Data Types - Arrays, List,Vectors,Operations,Data Frames and Descriptive Statistics |  | Introduction to RPA, Introduction to UI Path and Installed UI path tool | * UiPath – Understanding User Interface Components *Recording and Playback functionality. *Automating the task of copying data from a website and writing into excel file. | *Variables, Data Types and Activities in Ui Path *Basic exercises in UI Path studio | 1. Explored RE Framework Concepts in UI Path. | 1. Explored RE Framework Concepts in UI Path. | 1. Explored RE Framework Concepts in UI Path. | UIPATH STUDIO – DATA SCRAPING AND SCREEN SCRAPING | UiPath PDF Data Extraction and OCR Data Extraction | ON LEAVE
5 | Kamna | Database testing/ETL Testing, Jmeter,Selenium Framework | 1. KT Documents/Class Room session for ETL Testing 2. Jmeter : Process to setup the project and Documentaion | 1. KT Documents/Class Room session for ETL Testing 2. Jmeter : Process to setup the project and Documentaion | 1. ETL Testing : 28th May'19 2. Jmeter : 5th Jun'19 | 1. Git Hub repository creation 2. KT on GitHub to team Action Item for tomorrow : 1. Documentation for GitHub | On Leave | GiTHub document is added and sent for Review. Working DatabaseTesting related document with Ramesh | Working on Database testing document. Studying shell Scripting. I have scheduled a unix session . | Learning shell scripting/PPT preparation/Demo | 1. Learning Jmeter and its features/functionality used for performance testing. 2. Once done with all Jmeter feature will start POC and will design framework. | Practicing Selenium Framework using maven/TestNG/POM have uploaded the same in GIT as FirstMavenProject | Jmeter and its features/functionality used for performance/load testing. | Jmeter and its plugin manager( for Selenium Webdriver Support) also how to showing the performance dashboard in using non gui mode | 1. Was working on CI of Selenium Java project using Maven GIT Jenkins. 2. Was looking for Selenium and Jmeter framework. Couldnt find any useful tip. | 1. Jmeter PPT preparation.
6 | Shanth | RPA Automation, DevOps stacks involving selenium automation | RPA primer for the team to get started on using RPA tool(UiPath), User friendly documentation for the team to use in house published STAF framework for selenium automation | Build team capability to work on UiPath RPA tool, Provide inhouse expertise to leverage published automation framework for open source selenium along with Jenkins and Github integration | 1. RPA primer -31st May 2. STAF framework -7th June